## Jira Backlog
ID | Product | Epic | Issue Type | Summary | Description / Task | Acceptance Criteria | Priority | Dependencies | Est. Hours | Story Points | Suggested Sprint | Module | Technical Notes
ERP-MES-001 | ERP | Product Discovery & Pilot | Story | Factory workflow discovery and pilot definition | Interview target factories, map Excel/paper/WhatsApp workflows, select one vertical and pilot scope. | Pilot workflow maps, personas, MVP scope and success metrics approved. | High |  | 12 | 2 | S1 | Product Discovery & Pilot
ERP-MES-002 | ERP | Platform & Architecture Foundation | Story | Create Node.js TypeScript modular backend foundation | Set up module boundaries, configuration, error handling, dependency injection and API bootstrap. | Build, lint, test and start commands work; module structure documented. | High |  | 16 | 2 | S1 | Platform & Architecture Foundation
ERP-MES-003 | ERP | Platform & Architecture Foundation | Story | Create React TypeScript frontend foundation | Set up routing, module structure, API client, shared components and environment configuration. | Frontend builds and has authenticated shell/navigation. | High | EP02-1 | 16 | 2 | S1 | Platform & Architecture Foundation
ERP-MES-004 | ERP | Platform & Architecture Foundation | Story | Adopt MUI design system | Define theme, forms, dialogs, layout, notifications and reusable controls. | All core screens can use shared MUI components. | High | EP02-3 | 14 | 2 | S1 | Platform & Architecture Foundation
ERP-MES-005 | ERP | Platform & Architecture Foundation | Story | Adopt AG Grid for tabular business screens | Create reusable grid wrapper with sorting, filtering, paging, column state and export hooks. | Grid wrapper is reusable across master and transaction screens. | High | EP02-3 | 14 | 2 | S1 | Platform & Architecture Foundation
ERP-MES-006 | ERP | Platform & Architecture Foundation | Story | Define Repository Pattern and SOLID conventions | Document Controller→Service→Repository→DB flow and interface rules. | Architecture guideline and sample module approved. | High | EP02-1 | 8 | 1 | S1 | Platform & Architecture Foundation
ERP-MES-007 | ERP | Platform & Architecture Foundation | Story | Define Stored Procedure and SQL conventions | Define naming, parameters, transaction boundaries, versioning and parameterized SQL rules. | SP/SQL standards documented and sample procedures reviewed. | High | EP02-1 | 8 | 1 | S1 | Platform & Architecture Foundation | Repository interface -> implementation -> parameterized SQL/SP; no ORM; transaction integrity in DB.
ERP-MES-008 | ERP | Platform & Architecture Foundation | Story | Create OpenAPI API documentation | Expose versioned REST API documentation and examples. | OpenAPI document is generated and accessible in non-production environments. | Medium | EP02-1 | 8 | 1 | S1 | Platform & Architecture Foundation
ERP-MES-009 | ERP | Customer DB Provisioning & Isolation | Story | Create central control database | Store tenants, subscriptions, plans, features and database registry metadata only. | Control DB schema exists and contains no customer business transactions. | Critical | EP02-6 | 16 | 2 | S1 | Customer DB Provisioning & Isolation | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-010 | ERP | Customer DB Provisioning & Isolation | Story | Create tenant database registry | Track customer DB server, database identifier, status, schema version and health metadata without exposing credentials. | Registry supports active/inactive/maintenance states. | Critical | EP03-9 | 10 | 2 | S1 | Customer DB Provisioning & Isolation | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-011 | ERP | Customer DB Provisioning & Isolation | Story | Build customer database provisioning service | Provision a dedicated PostgreSQL database for every customer. | New customer receives isolated database and provisioning status. | Critical | EP03-10 | 24 | 3 | S2 | Customer DB Provisioning & Isolation | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-012 | ERP | Customer DB Provisioning & Isolation | Story | Build tenant DB migration runner | Run versioned schema migrations against each customer database. | Provisioned DB reaches expected schema version automatically. | Critical | EP03-11 | 20 | 3 | S2 | Customer DB Provisioning & Isolation | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-013 | ERP | Customer DB Provisioning & Isolation | Story | Seed default roles and master data per customer DB | Seed only safe defaults after provisioning. | Initial customer admin can log in with required baseline configuration. | High | EP03-12 | 12 | 2 | S2 | Customer DB Provisioning & Isolation | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-014 | ERP | Customer DB Provisioning & Isolation | Story | Implement server-side tenant resolution | Resolve tenant/database from authenticated identity and membership; never trust browser DB identifiers. | Cross-tenant database selection tests pass. | Critical | EP04-1 | 20 | 3 | S2 | Customer DB Provisioning & Isolation | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-015 | ERP | Customer DB Provisioning & Isolation | Story | Build tenant DB connection manager and pooling | Create secure per-tenant pool lifecycle, limits and idle cleanup. | Connections are isolated, bounded and recycled safely. | Critical | EP03-14 | 24 | 3 | S2 | Customer DB Provisioning & Isolation | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-016 | ERP | Customer DB Provisioning & Isolation | Story | Implement tenant database health checks | Check connectivity, schema version, pool health and service status. | Admin can see customer DB health and last successful check. | High | EP03-15 | 12 | 2 | S3 | Customer DB Provisioning & Isolation | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-017 | ERP | Customer DB Provisioning & Isolation | Story | Implement customer DB backup strategy | Define automated backup, retention and restore process per customer database. | Backup status and retention policy are documented and testable. | Critical | EP19-5 | 20 | 3 | S3 | Customer DB Provisioning & Isolation | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-018 | ERP | Customer DB Provisioning & Isolation | Story | Test cross-customer database isolation | Automate tests ensuring customer A can never read/write customer B business data. | Isolation suite passes in CI. | Critical | EP03-14 | 20 | 3 | S3 | Customer DB Provisioning & Isolation | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-019 | ERP | Customer DB Provisioning & Isolation | Story | Implement customer DB credential rotation | Rotate credentials without exposing secrets to application users. | Rotation can occur with controlled connection refresh. | High | EP03-15 | 16 | 2 | S4 | Customer DB Provisioning & Isolation | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-020 | ERP | Customer DB Provisioning & Isolation | Story | Implement customer data export package | Export customer-owned data in structured portable formats. | Authorized export produces complete customer package and audit entry. | High | EP16-5 | 24 | 3 | S4 | Customer DB Provisioning & Isolation | Support authenticated download; tenant context; audit; large-file async path where applicable.
ERP-MES-021 | ERP | Authentication & RBAC | Story | Implement authentication and refresh tokens | Secure login, refresh and logout flow. | Tokens expire, refresh works and revoked sessions cannot authenticate. | Critical | EP02-1 | 20 | 3 | S2 | Authentication & RBAC
ERP-MES-022 | ERP | Authentication & RBAC | Story | Implement RBAC and permission matrix | Create roles and granular module/action permissions. | Unauthorized actions return 403 and UI hides unavailable actions. | Critical | EP04-21 | 24 | 3 | S2 | Authentication & RBAC
ERP-MES-023 | ERP | Authentication & RBAC | Story | Implement session/device management | Allow administrators to revoke sessions and review active sessions. | Revoked sessions cannot access protected APIs. | High | EP04-21 | 16 | 2 | S3 | Authentication & RBAC
ERP-MES-024 | ERP | Master Data | Story | Customer, supplier and contact master | CRUD and search using MUI forms and AG Grid. | Create/edit/search/archive works with validation and audit. | High | EP03-13 | 20 | 3 | S3 | Master Data
ERP-MES-025 | ERP | Master Data | Story | Item/product master | Manage raw material, WIP, finished goods, units, categories and attributes. | Item lifecycle and validation are enforced. | Critical | EP03-13 | 24 | 3 | S3 | Master Data
ERP-MES-026 | ERP | Master Data | Story | Warehouse/location master | Manage plants, warehouses, bins and storage locations. | Inventory transactions can reference valid locations. | High | EP05-25 | 16 | 2 | S3 | Master Data
ERP-MES-027 | ERP | BOM & Routing | Story | BOM management | Create multi-level BOM with versions and effective dates. | BOM can be activated and exploded deterministically. | Critical | EP05-26 | 24 | 3 | S4 | BOM & Routing
ERP-MES-028 | ERP | BOM & Routing | Story | Routing and operation master | Define operations, sequence, work centers and standard times. | Production order can reference routing version. | High | EP05-26 | 20 | 3 | S4 | BOM & Routing
ERP-MES-029 | ERP | Procurement | Story | Purchase requisition | Create and approve internal material requests. | Approval state and audit trail are maintained. | High | EP05-27 | 18 | 3 | S5 | Procurement
ERP-MES-030 | ERP | Procurement | Story | Purchase order | Create, approve and revise purchase orders. | PO totals, status and supplier validation work. | Critical | EP07-28 | 24 | 3 | S5 | Procurement
ERP-MES-031 | ERP | Procurement | Story | Goods receipt with stored procedure | Receive material atomically and create inventory ledger entries. | Partial receipt, over-receipt rules and transaction rollback are handled. | Critical | EP07-29 | 28 | 4 | S5 | Procurement | Repository interface -> implementation -> parameterized SQL/SP; no ORM; transaction integrity in DB.
ERP-MES-032 | ERP | Inventory & Traceability | Story | Immutable inventory transaction ledger | Create append-only stock movement ledger. | Every stock movement has source, user, timestamp and quantity. | Critical | EP07-30 | 28 | 4 | S5 | Inventory & Traceability
ERP-MES-033 | ERP | Inventory & Traceability | Story | Inventory balance and availability | Provide current and available stock by item/location/batch. | Balances reconcile to ledger. | Critical | EP08-31 | 24 | 3 | S6 | Inventory & Traceability
ERP-MES-034 | ERP | Inventory & Traceability | Story | Stock transfer | Transfer stock between locations with atomic SP. | Source and destination balances update together or neither does. | High | EP08-32 | 20 | 3 | S6 | Inventory & Traceability
ERP-MES-035 | ERP | Inventory & Traceability | Story | Material issue and return | Issue/return material to production orders. | Ledger and production consumption remain consistent. | Critical | EP08-32 | 24 | 3 | S6 | Inventory & Traceability
ERP-MES-036 | ERP | Inventory & Traceability | Story | Batch/lot traceability | Track lot numbers, expiry and source/usage links. | Forward/backward traceability report works. | High | EP08-31 | 28 | 4 | S7 | Inventory & Traceability
ERP-MES-037 | ERP | Sales & Dispatch | Story | Sales order | Create and approve customer sales orders. | Order lifecycle and inventory checks work. | High | EP05-25 | 24 | 3 | S7 | Sales & Dispatch
ERP-MES-038 | ERP | Sales & Dispatch | Story | Delivery/dispatch | Create delivery and issue finished goods. | Dispatch creates correct inventory transaction. | High | EP09-39 | 24 | 3 | S8 | Sales & Dispatch
ERP-MES-039 | ERP | Production Planning | Story | Production plan | Create production plan by demand/date/priority. | Plan can be approved and converted to production orders. | High | EP09-40 | 20 | 3 | S8 | Production Planning
ERP-MES-040 | ERP | Production Planning | Story | Production order creation and BOM explosion | Create production order with required materials and operations. | Material requirements are calculated from active BOM version. | Critical | EP06-37 | 28 | 4 | S8 | Production Planning
ERP-MES-041 | ERP | Production Planning | Story | Material shortage calculation | Compare requirements, stock and open supply. | Shortage report identifies required purchase/transfer quantities. | High | EP10-42 | 20 | 3 | S9 | Production Planning
ERP-MES-042 | ERP | Production Planning | Story | Production order release | Release order after validation and approvals. | Released order is eligible for material issue/MES handoff. | Critical | EP10-42 | 16 | 2 | S9 | Production Planning
ERP-MES-043 | ERP | Basic Quality | Story | Incoming inspection | Capture inspection parameters and accept/reject receipt. | Rejected quantities are blocked or routed correctly. | High | EP07-30 | 22 | 3 | S9 | Basic Quality
ERP-MES-044 | ERP | Basic Quality | Story | In-process and final inspection | Capture production quality results and disposition. | Inspection status is linked to production output. | High | EP10-45 | 24 | 3 | S10 | Basic Quality
ERP-MES-045 | ERP | Basic Quality | Story | NCR and corrective action | Record nonconformance, disposition and corrective actions. | NCR lifecycle and audit trail work. | Medium | EP11-46 | 20 | 3 | S10 | Basic Quality
ERP-MES-046 | ERP | Manufacturing Costing | Story | Manufacturing cost calculation | Calculate material, labor, machine and overhead components. | Cost breakdown is explainable and reportable. | Medium | EP10-45 | 28 | 4 | S11 | Manufacturing Costing
ERP-MES-047 | ERP | Manufacturing Costing | Story | Actual vs standard cost variance | Compare expected and actual manufacturing cost. | Variance report identifies major drivers. | Medium | EP12-49 | 20 | 3 | S11 | Manufacturing Costing
ERP-MES-048 | ERP | Workflow & Customization | Story | Configurable approval workflow | Configure approval steps by document type. | Workflow is data/config driven, not customer-specific code. | High | EP04-22 | 28 | 4 | S11 | Workflow & Customization
ERP-MES-049 | ERP | Workflow & Customization | Story | Custom fields framework | Allow configured custom fields on selected master/transaction entities. | No customer-specific code fork is required for a new field. | Medium | EP13-51 | 24 | 3 | S12 | Workflow & Customization
ERP-MES-050 | ERP | Workflow & Customization | Story | Feature flags and optional modules | Enable/disable features per customer. | Disabled features are inaccessible through UI and API. | High | EP03-13 | 20 | 3 | S12 | Workflow & Customization
ERP-MES-051 | ERP | Dashboards & Reporting | Story | Owner dashboard | Show sales, stock, production, rejection and pending purchase KPIs. | Dashboard respects permissions and refreshes from tenant DB. | High | EP08-34 | 24 | 3 | S12 | Dashboards & Reporting
ERP-MES-052 | ERP | Dashboards & Reporting | Story | Inventory and production reports | Create filterable reports using AG Grid. | Reports support date/item/location filters and pagination. | High | EP08-34 | 24 | 3 | S13 | Dashboards & Reporting
ERP-MES-053 | ERP | PDF Reports & Documents | Story | PDF report engine | Generate printable PDF reports server-side. | PDF output has company branding, filters, date and generated-by metadata. | High | EP14-54 | 28 | 4 | S13 | PDF Reports & Documents | Support authenticated download; tenant context; audit; large-file async path where applicable.
ERP-MES-054 | ERP | PDF Reports & Documents | Story | PDF document templates | Create reusable templates for PO, GRN, SO, delivery and production documents. | Templates support customer branding and configurable fields. | Medium | EP15-57 | 28 | 4 | S14 | PDF Reports & Documents | Support authenticated download; tenant context; audit; large-file async path where applicable.
ERP-MES-055 | ERP | PDF Reports & Documents | Story | PDF download and secure access | Provide authenticated PDF download endpoints. | Only authorized users can download tenant documents. | High | EP15-58 | 16 | 2 | S14 | PDF Reports & Documents | Support authenticated download; tenant context; audit; large-file async path where applicable.
ERP-MES-056 | ERP | Excel/CSV Export & Data Export | Story | Excel export framework | Export AG Grid/report datasets to XLSX with correct types and headers. | Large exports do not block request threads and preserve filters. | High | EP14-55 | 24 | 3 | S13 | Excel/CSV Export & Data Export | Support authenticated download; tenant context; audit; large-file async path where applicable.
ERP-MES-057 | ERP | Excel/CSV Export & Data Export | Story | CSV export framework | Export datasets to CSV with UTF-8 and safe escaping. | CSV opens correctly in spreadsheet applications. | Medium | EP16-60 | 12 | 2 | S14 | Excel/CSV Export & Data Export | Support authenticated download; tenant context; audit; large-file async path where applicable.
ERP-MES-058 | ERP | Excel/CSV Export & Data Export | Story | Asynchronous large export jobs | Queue large PDF/Excel/CSV exports to a worker. | User can see export status and download completed file securely. | High | EP20-70 | 28 | 4 | S15 | Excel/CSV Export & Data Export | Support authenticated download; tenant context; audit; large-file async path where applicable.
ERP-MES-059 | ERP | Excel/CSV Export & Data Export | Story | Export audit trail | Record who exported what, when, filters and file type. | Audit report shows export history. | High | EP18-65 | 12 | 2 | S15 | Excel/CSV Export & Data Export | Support authenticated download; tenant context; audit; large-file async path where applicable.
ERP-MES-060 | ERP | SaaS Administration & Subscription | Story | SaaS customer onboarding admin | Admin UI for creating customer, plan and provisioning status. | Onboarding creates tenant and dedicated DB through workflow. | Critical | EP03-11 | 24 | 3 | S4 | SaaS Administration & Subscription
ERP-MES-061 | ERP | SaaS Administration & Subscription | Story | Subscription plan and feature management | Manage plans, limits and enabled modules. | Plan changes update feature access without code deployment. | Medium | EP13-52 | 20 | 3 | S15 | SaaS Administration & Subscription
ERP-MES-062 | ERP | Security, Audit & Compliance | Story | Audit logging | Log security-sensitive and business-critical actions. | Audit events include actor, action, entity, timestamp and correlation ID. | Critical | EP04-21 | 24 | 3 | S4 | Security, Audit & Compliance
ERP-MES-063 | ERP | Security, Audit & Compliance | Story | API rate limiting | Protect authentication and expensive endpoints. | Limits are configurable and return standard retry information. | High | EP02-8 | 16 | 2 | S4 | Security, Audit & Compliance
ERP-MES-064 | ERP | Security, Audit & Compliance | Story | Input validation and secure SQL | Centralize validation and prohibit SQL concatenation. | Security tests cover injection and invalid payloads. | Critical | EP02-7 | 20 | 3 | S4 | Security, Audit & Compliance | Repository interface -> implementation -> parameterized SQL/SP; no ORM; transaction integrity in DB.
ERP-MES-065 | ERP | Security, Audit & Compliance | Story | Security headers and HTTPS enforcement | Apply secure headers and production TLS configuration. | Security headers are validated in deployment checks. | High | EP20-75 | 12 | 2 | S5 | Security, Audit & Compliance
ERP-MES-066 | ERP | Files, Storage & Backup | Story | Azure Blob tenant-scoped storage | Store PDFs/attachments under customer-specific paths and authorization. | A user cannot access another customer's files. | High | EP15-59 | 20 | 3 | S15 | Files, Storage & Backup | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-067 | ERP | Files, Storage & Backup | Story | File upload validation | Validate file size/type/name and malware scanning integration point. | Unsafe uploads are rejected and events audited. | High | EP19-76 | 16 | 2 | S15 | Files, Storage & Backup
ERP-MES-068 | ERP | Deployment, CI/CD & Observability | Story | Dockerize frontend and API | Create production-ready Docker images. | Images build reproducibly and run with non-root/default secure settings where supported. | High | EP02-2 | 20 | 3 | S2 | Deployment, CI/CD & Observability
ERP-MES-069 | ERP | Deployment, CI/CD & Observability | Story | Docker Compose local environment | Provide API, frontend, PostgreSQL/control DB and Redis development stack. | One command starts local environment and health checks pass. | High | EP20-80 | 12 | 2 | S2 | Deployment, CI/CD & Observability
ERP-MES-070 | ERP | Deployment, CI/CD & Observability | Story | GitHub Actions CI/CD | Build, test, lint, scan and deploy Docker images. | Protected branches require successful CI. | High | EP20-79 | 24 | 3 | S3 | Deployment, CI/CD & Observability
ERP-MES-071 | ERP | Deployment, CI/CD & Observability | Story | Railway deployment topology | Deploy frontend, API, worker and Redis with environment separation. | Services have health checks, secrets and documented rollback. | High | EP20-82 | 20 | 3 | S4 | Deployment, CI/CD & Observability
ERP-MES-072 | ERP | Deployment, CI/CD & Observability | Story | Centralized structured logging | Implement JSON logs, correlation IDs and error tracking. | Requests can be traced across API, worker and DB operations. | High | EP20-83 | 20 | 3 | S5 | Deployment, CI/CD & Observability
ERP-MES-073 | ERP | Deployment, CI/CD & Observability | Story | Monitoring and alerting | Monitor API health, worker queues, DB health and error rates. | Critical failures generate actionable alerts. | Medium | EP20-84 | 20 | 3 | S6 | Deployment, CI/CD & Observability
ERP-MES-074 | ERP | ERP Customer Pilot & Hardening | Story | Pilot customer UAT | Run end-to-end workflows with first real customer. | Critical business flows pass UAT and issues are prioritized. | Critical | EP14-54 | 40 | 5 | S16 | ERP Customer Pilot & Hardening
ERP-MES-075 | MES | MES Foundation | Story | MES separate application foundation | Create independent MES Node/React codebase and deployment. | MES can run independently of ERP. | High | EP02-1 | 24 | 3 | S17 | MES Foundation | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-076 | MES | MES Identity & Operator | Story | MES operator authentication and role mapping | Support operator/supervisor roles and secure sessions. | Operators can access only assigned shop-floor functions. | High | EP22-90 | 20 | 3 | S17 | MES Identity & Operator | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-077 | MES | MES Work Centers, Machines & Shifts | Story | Work center and machine master | Manage machines, work centers, capabilities and status. | Execution can select valid work center/machine. | High | EP22-90 | 20 | 3 | S18 | MES Work Centers, Machines & Shifts | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-078 | MES | MES Work Centers, Machines & Shifts | Story | Shift and operator assignment | Manage shifts and assign operators. | Execution records correct shift/operator. | High | EP24-92 | 16 | 2 | S18 | MES Work Centers, Machines & Shifts | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-079 | MES | MES Production Execution | Story | MES production order queue | Display released jobs received from ERP. | Operators see priority, product, quantity and operation. | Critical | EP29-98 | 20 | 3 | S19 | MES Production Execution | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-080 | MES | MES Production Execution | Story | Start/pause/resume/complete operation | Capture operation execution state and timestamps. | Invalid state transitions are blocked. | Critical | EP25-94 | 28 | 4 | S19 | MES Production Execution | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-081 | MES | MES Production Execution | Story | Good/reject/scrap/rework quantities | Capture production disposition. | Quantities reconcile with planned/started quantities according to configured rules. | Critical | EP25-96 | 24 | 3 | S20 | MES Production Execution | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-082 | MES | MES Quality & Traceability | Story | MES quality execution | Capture in-process checks and defect results at operation. | Quality result links to job/operator/time. | High | EP11-47 | 24 | 3 | S20 | MES Quality & Traceability | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-083 | MES | MES Quality & Traceability | Story | Production traceability genealogy | Track material lot to production output and operation. | Traceability can be queried forward and backward. | High | EP25-97 | 28 | 4 | S21 | MES Quality & Traceability | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-084 | MES | MES Downtime & OEE | Story | Downtime capture and reason codes | Record downtime start/end/reason. | Downtime duration and reason totals are accurate. | High | EP24-93 | 20 | 3 | S21 | MES Downtime & OEE | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-085 | MES | MES Downtime & OEE | Story | OEE calculation | Calculate availability, performance and quality with configurable definitions. | OEE dashboard shows drill-down to losses. | Medium | EP27-103 | 32 | 4 | S22 | MES Downtime & OEE | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-086 | MES | MES Shop-Floor UI | Story | Shop-floor tablet UI | Create large-touch controls and simplified operator workflow. | Core execution works on tablet-sized screens. | High | EP25-96 | 28 | 4 | S19 | MES Shop-Floor UI | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-087 | MES | MES Shop-Floor UI | Story | QR job/order scanning | Scan job QR/barcode to open execution. | Invalid/unauthorized jobs are rejected safely. | Medium | EP28-105 | 20 | 3 | S22 | MES Shop-Floor UI | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-088 | MES | ERP-MES API Integration | Story | Versioned ERP-MES API contract | Define production order, master sync and result contracts. | Contract is documented in OpenAPI and versioned. | Critical | EP22-90 | 24 | 3 | S18 | ERP-MES API Integration | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-089 | MES | ERP-MES API Integration | Story | ERP to MES production order API | Send released production orders to MES. | Idempotent create/update behavior is implemented. | Critical | EP29-108 | 28 | 4 | S19 | ERP-MES API Integration | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-090 | MES | ERP-MES API Integration | Story | MES to ERP production result API | Send good/reject/scrap/complete results back to ERP. | ERP updates are idempotent and auditable. | Critical | EP29-109 | 28 | 4 | S21 | ERP-MES API Integration | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-091 | MES | ERP-MES API Integration | Story | Integration retry and dead-letter handling | Retry transient failures and retain failed messages for investigation. | No data loss on temporary API failures. | High | EP29-110 | 24 | 3 | S22 | ERP-MES API Integration | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-092 | MES | ERP-MES API Integration | Story | Integration audit and monitoring | Track every ERP-MES request/response/correlation ID. | Support can trace integration failures end to end. | High | EP29-111 | 20 | 3 | S22 | ERP-MES API Integration | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-093 | MES | MES Data Export & Reports | Story | MES PDF production report | Generate printable shift/job/production reports. | PDF contains planned, actual, reject, scrap, downtime and sign-off fields. | Medium | EP27-104 | 20 | 3 | S23 | MES Data Export & Reports | Support authenticated download; tenant context; audit; large-file async path where applicable.
ERP-MES-094 | MES | MES Data Export & Reports | Story | MES Excel/CSV export | Export production, downtime, quality and OEE datasets. | Exports preserve filters and tenant/security context. | Medium | EP30-114 | 20 | 3 | S23 | MES Data Export & Reports | Support authenticated download; tenant context; audit; large-file async path where applicable.
ERP-MES-095 | MES | IoT/Machine Gateway Future | Story | Machine gateway architecture spike | Define future gateway boundary without coupling MES to PLC protocols. | Architecture document covers MQTT/OPC-UA adapter boundary. | Low | EP22-90 | 12 | 2 | S24 | IoT/Machine Gateway Future | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-096 | MES | IoT/Machine Gateway Future | Story | MQTT/OPC-UA integration spike | Prototype machine data ingestion in isolated environment. | Prototype demonstrates secure ingestion without impacting core MES. | Low | EP31-116 | 24 | 3 | S25 | IoT/Machine Gateway Future | MES remains independently deployable; integrate with ERP through versioned APIs, not shared tables.
ERP-MES-097 | Platform | Future Analytics & AI | Story | Future analytics data model | Define reporting/event model for future analytics without adding AI to MVP. | Data requirements and retention approach documented. | Low | EP14-55 | 12 | 2 | S26 | Future Analytics & AI
ERP-MES-098 | Platform | Future Analytics & AI | Story | Future AI opportunities backlog | Identify forecasting, anomaly detection, scheduling and quality use cases from real data. | AI use cases are prioritized only after sufficient operational data exists. | Low | EP32-118 | 12 | 2 | S26 | Future Analytics & AI
ERP-MES-099 | ERP | Platform & Architecture Foundation | Task | Define API error contract | Standardize error codes, correlation IDs and validation response format. | All APIs use the same error envelope. | High | EP02-8 | 8 | 1 | S2 | Platform & Architecture Foundation
ERP-MES-100 | ERP | Platform & Architecture Foundation | Task | Define pagination/filter/sort contract | Standardize AG Grid-compatible server-side querying. | All large grids use consistent query parameters. | High | EP02-8 | 8 | 1 | S2 | Platform & Architecture Foundation
ERP-MES-101 | ERP | Customer DB Provisioning & Isolation | Task | Schema version registry per customer DB | Record migration version and compatibility status. | Admin can identify outdated customer schemas. | Critical | EP03-12 | 10 | 2 | S3 | Customer DB Provisioning & Isolation | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-102 | ERP | Customer DB Provisioning & Isolation | Task | Customer DB maintenance mode | Temporarily block business operations during migrations/restores. | Users see maintenance state and writes are blocked safely. | High | EP03-16 | 12 | 2 | S3 | Customer DB Provisioning & Isolation | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-103 | ERP | Customer DB Provisioning & Isolation | Task | Customer DB restore drill | Test restoring a customer DB into a temporary environment. | Restore procedure is repeatable and documented. | Critical | EP03-17 | 16 | 2 | S4 | Customer DB Provisioning & Isolation | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-104 | ERP | Customer DB Provisioning & Isolation | Task | Customer DB deletion/retention workflow | Implement authorized offboarding with retention safeguards. | Deletion requires approval, audit and backup policy compliance. | High | EP03-17 | 16 | 2 | S16 | Customer DB Provisioning & Isolation | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-105 | ERP | PDF Reports & Documents | Task | PDF pagination and page-break rules | Ensure tables, headers and totals render correctly over multiple pages. | Generated PDFs are readable and deterministic. | Medium | EP15-58 | 16 | 2 | S14 | PDF Reports & Documents | Support authenticated download; tenant context; audit; large-file async path where applicable.
ERP-MES-106 | ERP | PDF Reports & Documents | Task | PDF report download audit | Log report name, filters, tenant, user and timestamp. | Every sensitive PDF download is auditable. | High | EP18-65 | 8 | 1 | S15 | PDF Reports & Documents | Support authenticated download; tenant context; audit; large-file async path where applicable.
ERP-MES-107 | ERP | Excel/CSV Export & Data Export | Task | Excel formatting and data typing | Format dates, decimals, IDs and large datasets correctly. | Excel export is usable without manual cleanup. | Medium | EP16-60 | 12 | 2 | S14 | Excel/CSV Export & Data Export | Support authenticated download; tenant context; audit; large-file async path where applicable.
ERP-MES-108 | ERP | Excel/CSV Export & Data Export | Task | Export permission model | Separate view permission from export permission for sensitive data. | Unauthorized export requests are rejected server-side. | High | EP18-65 | 10 | 2 | S15 | Excel/CSV Export & Data Export | Support authenticated download; tenant context; audit; large-file async path where applicable.
ERP-MES-109 | ERP | Deployment, CI/CD & Observability | Task | Database migration CI validation | Run migration scripts against clean PostgreSQL in CI. | Migrations can create a fresh customer DB successfully. | Critical | EP03-12 | 16 | 2 | S3 | Deployment, CI/CD & Observability | Dedicated PostgreSQL DB per customer; central control DB stores metadata only; credentials server-side.
ERP-MES-110 | ERP | Deployment, CI/CD & Observability | Task | Container image vulnerability scanning | Scan images and fail builds for configured critical findings. | CI publishes scan results and blocks policy violations. | High | EP20-82 | 10 | 2 | S4 | Deployment, CI/CD & Observability
ERP-MES-111 | ERP | Deployment, CI/CD & Observability | Task | Secrets management policy | Document Railway/Azure secret handling and rotation rules. | No credentials are committed to source control. | Critical | EP20-83 | 8 | 1 | S2 | Deployment, CI/CD & Observability
ERP-MES-112 | ERP | Deployment, CI/CD & Observability | Task | Backup/restore monitoring | Alert on failed backups and stale backup timestamps. | Operations dashboard shows backup health. | High | EP03-17 | 12 | 2 | S6 | Deployment, CI/CD & Observability
ERP-MES-113 | ERP | Security, Audit & Compliance | Task | Security test suite | Automate auth, authorization, injection, tenant isolation and export access tests. | Security suite runs in CI for critical APIs. | Critical | EP18-65 | 24 | 3 | S6 | Security, Audit & Compliance
ERP-MES-114 | ERP | ERP Customer Pilot & Hardening | Task | ERP production readiness checklist | Verify security, backups, monitoring, export, PDF, DB isolation and rollback before pilot. | Go-live checklist is signed off. | Critical | EP21-87 | 16 | 2 | S16 | ERP Customer Pilot & Hardening

## Epic Summary
Epic ID | Epic | Product | Items | Estimated Hours | Priority Focus
EP01 | Product Discovery & Pilot | ERP | 1 | 12 | Core / as defined in backlog
EP02 | Platform & Architecture Foundation | ERP | 9 | 100 | Core / as defined in backlog
EP03 | Customer DB Provisioning & Isolation | ERP | 16 | 272 | Core / as defined in backlog
EP04 | Authentication & RBAC | ERP | 3 | 60 | Core / as defined in backlog
EP05 | Master Data | ERP | 3 | 60 | Core / as defined in backlog
EP06 | BOM & Routing | ERP | 2 | 44 | Core / as defined in backlog
EP07 | Procurement | ERP | 3 | 70 | Core / as defined in backlog
EP08 | Inventory & Traceability | ERP | 5 | 124 | Core / as defined in backlog
EP09 | Sales & Dispatch | ERP | 2 | 48 | Core / as defined in backlog
EP10 | Production Planning | ERP | 4 | 84 | Core / as defined in backlog
EP11 | Basic Quality | ERP | 3 | 66 | Core / as defined in backlog
EP12 | Manufacturing Costing | ERP | 2 | 48 | Core / as defined in backlog
EP13 | Workflow & Customization | ERP | 3 | 72 | Core / as defined in backlog
EP14 | Dashboards & Reporting | ERP | 2 | 48 | Core / as defined in backlog
EP15 | PDF Reports & Documents | ERP | 5 | 96 | Core / as defined in backlog
EP16 | Excel/CSV Export & Data Export | ERP | 6 | 98 | Core / as defined in backlog
EP17 | SaaS Administration & Subscription | ERP | 2 | 44 | Core / as defined in backlog
EP18 | Security, Audit & Compliance | ERP | 5 | 96 | Core / as defined in backlog
EP19 | Files, Storage & Backup | ERP | 2 | 36 | Core / as defined in backlog
EP20 | Deployment, CI/CD & Observability | ERP | 10 | 162 | Core / as defined in backlog
EP21 | ERP Customer Pilot & Hardening | ERP | 2 | 56 | Core / as defined in backlog
EP22 | MES Foundation | MES | 1 | 24 | Core / as defined in backlog
EP23 | MES Identity & Operator | MES | 1 | 20 | Core / as defined in backlog
EP24 | MES Work Centers, Machines & Shifts | MES | 2 | 36 | Core / as defined in backlog
EP25 | MES Production Execution | MES | 3 | 72 | Core / as defined in backlog
EP26 | MES Quality & Traceability | MES | 2 | 52 | Core / as defined in backlog
EP27 | MES Downtime & OEE | MES | 2 | 52 | Core / as defined in backlog
EP28 | MES Shop-Floor UI | MES | 2 | 48 | Core / as defined in backlog
EP29 | ERP-MES API Integration | MES | 5 | 124 | Core / as defined in backlog
EP30 | MES Data Export & Reports | MES | 2 | 40 | Core / as defined in backlog
EP31 | IoT/Machine Gateway Future | MES | 2 | 36 | Core / as defined in backlog
EP32 | Future Analytics & AI | Platform | 2 | 24 | Core / as defined in backlog

## Architecture
Area | Decision / Standard
Frontend | React + TypeScript + Material UI + AG Grid
Backend | Node.js + TypeScript REST API + OpenAPI
Design | SOLID + Controller -> Service -> Repository -> Database
ORM | None
Data access | Repository Pattern; parameterized SQL and Stored Procedures
Database | PostgreSQL
Tenant isolation | One dedicated PostgreSQL database per customer
Control DB | Tenants, subscriptions, plans, features, DB registry, identity metadata only
Business data | Stored only in customer-specific DB
Tenant resolution | Server-side from authenticated identity/membership; never from arbitrary browser DB ID
Files | Azure Blob Storage with tenant-scoped paths and authorization
Async | Redis + Node.js worker for large exports/background jobs
Deployment | Docker; Railway initially; architecture migration-ready for Azure
CI/CD | GitHub Actions
Security | JWT/refresh tokens, RBAC, validation, parameterized SQL, rate limiting, audit, HTTPS, secrets management
Reports | Server-side PDF generation; authenticated download and audit
Exports | XLSX/CSV export, server-side permission checks, async large exports
ERP/MES | Separate applications; no shared DB tables
Integration | Versioned REST APIs first; events/outbox-ready later
MES initial scope | Manual shop-floor execution first; no PLC/IoT dependency
Future | MQTT/OPC-UA, advanced analytics and AI after real operational data exists

## Definition of Done
Category | Definition of Done
Code | TypeScript compiles, lint passes, no dead code, SOLID boundaries respected.
API | OpenAPI updated, validation implemented, consistent error contract, authorization enforced.
Repository | Service depends on interface; DB access stays in repository; no ORM; SQL is parameterized.
Database | SP/SQL reviewed, indexes considered, transaction boundaries defined, migration included.
Tenant isolation | Automated test proves no cross-customer reads/writes/files/exports.
UI | MUI standards followed; AG Grid used for large datasets; loading/error/empty states included.
PDF | Report has correct filters, pagination, metadata and secure authorization.
Excel/CSV | Export respects permissions, filters, typing, encoding and large-data strategy.
Security | Auth/RBAC/security tests pass; secrets absent from source.
Operations | Docker build passes; logs/health checks/metrics available; rollback documented.
Testing | Unit, integration and critical end-to-end tests pass.
Documentation | API, DB migration, configuration and operational notes updated.

## PDF_Excel_Export
Feature | PDF | Excel/XLSX | CSV | Security / Technical
Inventory report | Yes | Yes | Yes | Tenant DB; view/export permission; audit
Purchase order | Yes | Yes | Yes | Authorized users only; PDF template
GRN | Yes | Yes | Yes | Document audit; tenant-scoped file
Sales order | Yes | Yes | Yes | Customer data protected
Delivery/dispatch | Yes | Yes | Yes | Inventory consistency
Production order | Yes | Yes | Yes | ERP/MES traceability
Production result | Yes | Yes | Yes | MES integration audit
Quality/NCR | Yes | Yes | Yes | Sensitive operational data
OEE/downtime | Yes | Yes | Yes | MES permissions and filters
Large report | Async | Async | Async | Redis/worker + secure temporary download
File retention | Configurable | Configurable | Configurable | Tenant-specific retention and cleanup